## Sample
Project Status Report - Q1 2026
Project: Customer Portal Redesign
Project Manager: Priya Nair
Status: On Track
Percent Complete: 68%
Milestone: Requirements Sign-off - Complete - Jan 15, 2026
Milestone: UI Design Approval - Complete - Feb 10, 2026
Milestone: Backend API Complete - In Progress - Due Mar 28, 2026
Milestone: QA Testing - Not Started - Due Apr 15, 2026
Milestone: Production Launch - Not Started - Due May 1, 2026
Risks: Third-party payment gateway integration delayed by vendor; mitigation in progress.
Notes: See attached one-pager memo for executive summary.